## GTM Brief
Field | Your Input
Goal (e.g., $1M ARR in 2Q)
Audience (ICP & Segments)
Positioning (For [who] that [job], our [product] is the [category] that [benefit] because [reason])
Launch tier (T1/T2/T3)
KPIs (primary/secondary/guardrails)
Routes to market (Direct/PLG/Channel/Marketplace)
Pricing & packaging hypothesis
Key dates (Beta, Code freeze, Content freeze, PR embargo, Launch)
Risks & mitigations (Top 5)
RACI (names)

## Task List
Phase | Task | Deliverable | Owner | Status | Start | Due | Dependencies | KPI Impact | Tier | Notes
0) GTM spine | Define problem/outcomes | One-page brief |  | Not started | 2025-10-11 | 2025-10-18 |  | North Star clarity | All
1) Research | Customer discovery (8–12 interviews/segment) | Interview notes, insights |  | Not started | 2025-10-11 | 2025-11-10 |  | Message-market fit | T1/T2
1) Research | Competitive mapping | Matrix & win/loss notes |  | Not started | 2025-10-11 | 2025-11-10 |  | Win rate ↑ | T1/T2
2) Product | Beta program | Cohort, success criteria, testimonials |  | Not started | 2025-10-11 | 2025-11-10 | MVP ready | Activation ↑ | T1/T2
2) Product | Telemetry & dashboards | Activation/retention/conversion dashboards |  | Not started | 2025-10-11 | 2025-11-10 |  | Insight velocity ↑ | All
3) Monetization | Price & package | Tier matrix, ROI calculator |  | Not started | 2025-10-11 | 2025-11-10 | Research inputs | Revenue ↑ | All
4) Narrative | Messaging hierarchy | Messaging doc (claim → pillars → features) |  | Not started | 2025-10-11 | 2025-11-10 | Discovery learnings | CTR ↑ | All
4) Narrative | Demo assets | 30/60/120s demo scripts & video |  | Not started | 2025-10-11 | 2025-12-10 |  | Conv. rate ↑ | All
5) Demand Gen | Channel plan | Weekly targets, audiences, exclusions |  | Not started | 2025-10-11 | 2025-11-10 | Messaging | Pipeline coverage | All
5) Demand Gen | Lead magnets | Templates/checklists/benchmarks |  | Not started | 2025-10-11 | 2025-11-10 | Narrative | MQLs ↑ | T1/T2
6) Sales | Enablement kit | Deck, battlecards, discovery bank, MAP |  | Not started | 2025-10-11 | 2025-11-10 | Narrative | SQL→Win ↑ | Sales-assisted
7) Success | Support readiness | Runbooks, macros, SLAs |  | Not started | 2025-10-11 | 2025-11-10 | Product readiness | CSAT ↑ | All
8) Legal | Policies & DPA | ToS/Privacy/DPA, trademark checks |  | Not started | 2025-10-11 | 2025-11-10 |  | Risk ↓ | All
9) Analytics | Experiment ledger | Hypothesis→variant→decision log |  | Not started | 2025-10-11 | 2025-11-10 |  | Learning rate ↑ | All
10) Ops | Go/No-Go | Checklist & owner map |  | Not started | 2025-10-11 | 2025-12-10 | All tracks green | Launch quality | All
11) Acceleration | Day 1–7 readout | Cohort analysis & fixes |  | Not started | 2025-10-18 | 2025-11-10 | Launch live | Retention/Activation ↑ | All

## Content BOM
Asset | Purpose | Channel | Owner | Status | Link | Due | Notes
Homepage hero + product page | Conversion | Website |  | Not started |  | 2025-11-10
Launch blog + technical deep-dive | Awareness & trust | Blog |  | Not started |  | 2025-11-10
90-sec demo video | Conversion assist | YouTube/Site |  | Not started |  | 2025-12-10
Sales deck + one-pager | Sales assist | Sales |  | Not started |  | 2025-11-10
Email sequences (announce/nurture/proof) | Activation | Email |  | Not started |  | 2025-11-10
2 ads (search + social) | Acquire demand | Paid |  | Not started |  | 2025-11-10
FAQ + help docs update | Self-serve success | Docs |  | Not started |  | 2025-11-10

## Demand Gen Plan
Channel | Tactics | Budget (USD) | Weekly Target | Primary KPIs | Notes
Owned | Homepage + blog cadence |  | 0 | Weekly sessions, CTR
Earned | PR + analyst briefings |  | 0 | Share of voice, backlinks
Paid | Search + social + retargeting |  | 0 | CAC, CTR, CVR
Partner | Marketplace listings + webinars |  | 0 | Partner-sourced pipeline

## Pricing Guardrails
Item | Value/Notes
Floor price
Target price
Walk-away
Discount bands by deal size/stage
Non-discount levers (term/prepay/bundle/volume/references)

## Launch Runbook
Timing | Step | Owner | Status
T-48h | Final UAT, content QA, link checks, tracking verification |  | Not started
T-24h | Code freeze, backups, press kit final |  | Not started
T-2h | Team stand-up, schedule posts, enable ads (paused) |  | Not started
T-0 | Flip feature flag, ads live, embargo lifts, live webinar |  | Not started
T+2h | Health check, funnel readout, support sync |  | Not started
T+24h | Debrief, issues list, next actions |  | Not started

## Metrics
Metric | Definition | Formula | Target | Source | Dashboard Link
Awareness | Reach, PR hits, share of voice | n/a | Targets per tier | PR/Analytics
Interest | CTR, demo requests, signups | n/a | Targets per segment | Site Analytics
Intent | SQLs/opps created, win rate | Sales velocity | Targets by stage | CRM
Activation | Time-to-value, onboarding completion | Activation rate | TTV target | Product analytics
Revenue | ARR/MRR, ASP, expansion, churn | CAC payback | Targets per plan | Billing/RevOps
Efficiency | CAC, payback, LTV/CAC | Formulas sheet | Targets per channel | Finance/RevOps

## Formulas
Metric | Formula | Notes
CAC payback (months) | CAC ÷ (ARPA × Gross Margin) | Use by channel and blended
Lead→SQL conversion | SQLs ÷ Leads
Sales velocity | (# opps × win rate × ASP) ÷ sales cycle length | Time unit must match cycle length
Activation rate | # users hitting 'aha' ÷ signups

## RACI
Deliverable | Responsible | Accountable | Consulted | Informed
Strategy & narrative | PMM/GM | PMM/GM | Product, Sales, Success | Execs, Partners
Product readiness | Product | Head of Product | PMM, Design | Execs
Channels & content | Growth/Marketing | Head of Growth | PMM, Data | Execs
Sales enablement | Sales | Head of Sales | PMM, Product | Execs
Onboarding & support | Success/Support | Head of CS | PMM, Product | Execs
Tracking & attribution | Data/RevOps | Head of RevOps | PMM, Marketing | Execs
Policies & pricing approvals | Legal/Finance | CFO/GC | PMM, Product | Execs

## Risk Register
Risk | Likelihood | Impact | Mitigation | Owner | Status
Scope creep | Medium | High | Tiering + content freeze dates |  | Open
Messaging drift | Medium | Medium | Single source of truth + reviewer checklist |  | Open
Mis-attribution of revenue | Low | High | UTM discipline + CRM required fields |  | Open
Support overload | Medium | High | Staged rollout + clear SLAs + status comms |  | Open
Pricing confusion | Medium | High | Crisp fences + calculator + examples |  | Open

## Launch Calendar
Date | Milestone | Owner | Status
2025-10-11 | Kickoff & GTM spine |  | Not started
2025-10-18 | Content & research mid-point |  | Not started
2025-11-10 | Beta wrap & pricing lock |  | Not started
2025-12-10 | Go/No-Go & launch |  | Not started

## Sales Enablement
Asset | Purpose | Owner | Link | Status
Deck | Storyline & ROI |  |  | Not started
Discovery question bank | Structured discovery |  |  | Not started
Battlecards | Competitive clarity |  |  | Not started
Demo script | Consistent demo |  |  | Not started
Mutual Action Plan template | Drive next steps |  |  | Not started

## Changelog
Refreshed At (local server time) | Notes
2025-10-11T03:02:42 | Version 2 export with current dates and new filenames