## Snapshot
Snapshot
**Risk:** YELLOW
**Tasks:** 16 total • **Done:** 0 (0%)
**Overdue:** 0 • **Due today:** 0 • **Next 3 days:** 4 • **Next 7 days:** 2
**Undated:** 0 • **Unowned:** 0

## Milestones
Date | Milestone | Owner | Status
2025-10-14 | Content & research checkpoint | Emmanuel Ngabire | Not started
2025-10-17 | Beta wrap & testimonials captured | Emmanuel Ngabire | Not started
2025-10-19 | Pricing lock & ROI calculator live | Emmanuel Ngabire | Not started
2025-10-22 | Go/No-Go readiness | Emmanuel Ngabire | Not started
2025-10-24 | Launch day | Emmanuel Ngabire | Not started

## Tasks
Bucket | Date | Phase | Task | Owner | Status
Next 3 Days | 2025-10-14 | 0) GTM spine | Define problem/outcomes | Emmanuel Ngabire | Not started
Next 3 Days | 2025-10-14 | 1) Research | Customer discovery (5–8 quick calls) | Emmanuel Ngabire | Not started
Next 3 Days | 2025-10-14 | 1) Research | Competitive mapping (lite) | Emmanuel Ngabire | Not started
Next 3 Days | 2025-10-14 | 4) Narrative | Messaging hierarchy | Emmanuel Ngabire | Not started
Days 4–7 | 2025-10-17 | 2) Product | Beta sanity check | Emmanuel Ngabire | Not started
Days 4–7 | 2025-10-17 | 2) Product | Telemetry essentials | Emmanuel Ngabire | Not started